## Sheet1
Risk ID | Risk Description | Affected Asset | Risk Category | Likelihood | Impact | Risk Level | Notes
R-01 | There is a risk that unauthorized access to customer data may occur due to the absence of authentication mechanisms. | Web Application / Database | Access Control | High | High | High | No authentication mechanism implemented; users can perform transactions without identity verification
R-02 | There is a risk of excessive privileged access due to developers having unrestricted access to database, deployment, and environment variables. | Multiple (DB, Render, GitHub) | Access Control | High | High | High | Developer has direct access to database, environment variables, and deployment platform
R-03 | There is a risk of exposure of sensitive data due to inconsistent encryption of PII fields. | MongoDB Database | Data Protection | High | High | High | Only email and phone are encrypted; name and address stored in plaintext
R-04 | There is a risk of credential compromise due to potential exposure of environment variables and secrets. | Environment Variables | Data Protection | High | High | High | Sensitive credentials (e.g., MONGO_URI, API keys) stored in environment variables with potential exposure risk
R-05 | There is a risk of unauthorized or untested changes being deployed due to lack of formal change management controls. | Deployment (Render / GitHub) | Change Management | High | Medium | High | No pull request approval or staging environment before production deployment
R-06 | There is a risk of inability to detect unauthorized activity due to lack of access and activity logging. | Logging System | Logging & Monitoring | Medium | High | High | No logging of user access or administrative actions; only system-level logs available
R-07 | There is a risk related to third-party dependency due to lack of formal vendor risk management for external services such as Stripe. | Third-Party Services | Third-Party Risk | Medium | Medium | Medium | Third-party services (Stripe, Cloudinary, Gmail) are used without formal vendor risk assessment